## Sheet1
การไฟฟ้าส่วนภูมิภาค รายละเอียดของงานเพื่อขออนุมัติเบิกจ่ายเงิน
งานก่อสร้างสถานีไฟฟ้าชนิด Outdoor AIS ระบบ 115-22 เควี, สายส่งระบบ 115 เควี (ภายใน) และระบบจำหน่าย 22 เควี ให้บริษัท มูราตะ อิเล็กทรอนิกส์ (ประเทศไทย) จำกัด จังหวัดลำพูน
| สัญญาเลขที่ กส2/2562 ลงวันที่ 24/06/2562 ผู้รับจ้าง บริษัท มูราตะ อิเล็กทรอนิกส์ (ประเทศไทย) จำกัด จังหวัดลำพูน | [8 empty] | ค่าอุปกรณ์และค่าขนส่ง | งวดที่ | 2
id | ลำดับที่ | รายละเอียด |  | งานตามสัญญา |  |  |  |  | รวมงานที่ส่งมอบแล้ว |  | ส่งมอบงานครั้งนี้
|  |  |  | จำนวน | หน่วย | ราคาอุปกรณ์/หน่วย (บาท) | ค่าขนส่ง/หน่วย (บาท) | เป็นเงิน (บาท) | จำนวน | เป็นเงิน (บาท) | จำนวน | เป็นเงิน (บาท)
299 |  | PART A อุปกรณ์สถานีไฟฟ้า
300 | 1 | 115 kV Tower incoming structure ( Take off structure )
301 |  | - | 115 kV. Take-off structure, beam. | 2 | Set | 30000000 | 200000 | 30200000 |  |  | 1 | 30200000
302 |  | - | 115 kV. Take-off structure, column. | 2 | Set | 150000 | 200000 | 700000 | 1 | 350000 | 3 | 1050000
303 |  | - | Insulator, suspension type, class 52-3, for 115 kV string assemblies. | 6 | Set
304 |  | - | 250 watt, area LED floodlight luminaires and accessories | 2 | Set
305 | 2 | 115 kV Disconnecting with grounding switch and support structure
306 |  | - | 123 kV, 1250A 40kA Disconnecting switch, three-pole, double side break with grounding | 1 | Set | By PEA | By PEA
307 |  |  | creepage 25 mm/kV., handle for cranking and tools
308 |  | - | 115 kV Disconnecting switch supporting structure | 1 | Set
309 |  | - | Operating platform | 2 | Set
310 | 3 | 115 kV Current transformer
311 |  | - | 115 kV Current transformer, single-phase, 4 cores, 40kA and creepage 25 mm/kV | 3 | Set | By PEA | By PEA
312 |  | - | 115 kV Current transformer supporting structure | 3 | Set
313 |  | - | Junction box for 115 kV current transformer | 1 | Unit
314 |  | - | Junction box supporting structure | 1 | Set
315 | 4 | 115 kV Inductive voltage transformer
316 |  | - | 115 kV Inductive voltage transformer, single-phase, 3 winding 40kA and creepage 25 mm/kV | 3 | Set | By PEA | By PEA
317 |  | - | 115 kV Inductive voltage transformer supporting structure | 3 | Set
318 |  | - | Junction box for 115 kV inductive voltage transformer | 1 | Unit
319 |  | - | Junction box supporting structure | 1 | Set
320 | 5 | 115 kV Gas circuit breaker (SF6)
321 |  | - | 115 kV Circuit-breaker, SF6 gas, three-pole, 3150A, 40 kA | 1 | Set | By PEA
322 |  | - | 115 kV Circuit-breaker supporting structure | 1 | Set
323 |  | - | Operating platform (2 step stairs) | 1 | Set
324 | 6 | 115 kV Control & protection board
325 |  | - | Transformer control and protection board | 1 | Unit | By PEA
326 |  | - | Outdoor alarm (horn & siren) | 1 | Set
327 | 7 | Power transformer
328 |  | - | 115/22 kV, 3 phase, ONAN/ONAF, 50/60 MVA, Dyn1, with automatic OLTC with | 1 | Unit | By PEA
329 |  |  | oil purifier for OLTC, CT core in MV for winding temp, AVR and N bushing for protection
330 |  | - | Local control cubicle with lamp indicator and annunciator | 1 | Unit | By PEA
331 |  | - | Loose supply for tap position indicator for OLTC and AVR, | 1 | Lot | By PEA
332 |  | - | 108 kV 10 kA Lightning arrester and counter with supporting on power transformer | 3 | Set | By PEA
333 | 8 | 22 kV Indoor air insulated switchgear (2,500 A, 25 kA, 1 Sec)
334 |  | - | 22 kV Incoming cubicle with potential transformer (2500A) | 1 | Unit | By PEA
335 |  | - | 22 kV Outgoing cubicle (630A 25kA) | 2 | Unit | By PEA
336 |  | - | 22 kV Load break switch cubicle with fuse 1 set | 1 | Lot | By PEA
337 |  | - | Arc detection system (fiber optic 3 compartment per 1 cubicle), | 1 | Lot | By PEA
338 |  | - | Wall plate for tool storage | 1 | Set | By PEA
339 | 9 | 22/0.4 kV Station service transformer
340 |  | - | Station service transformer, oil-immersed type,three-phase, 50 kVA, Dyn1 | 1 | Set
341 |  |  | 22,000-400/230 VAC with cable connection boxes, for outdoor installation.
342 | 10 | AC and DC distribution board
343 |  | - | AC distribution board (2 main CB, 80 A, 20 branch circuits) | 1 | Set
344 |  | - | DC distribution board (2 main CB, 40 A, 20 branch circuits) | 1 | Set
345 | 11 | Battery & battery charger for 125 VDC
346 |  | - | Sealed lead acid battery > 58 Ah 12V/block (125 Vdc) | 1 | Lot
347 |  | - | Batter charger 30 A with automatic dropper switch | 2 | Set
348 |  | - | Safety switch with fuse | 1 | Set
349 | 12 | Power cable & termination kit
350 |  | - | H.V. power cable, 9-1x500 sq.mm., 22 kV, for connecting between the incoming | 1 | Lot
351 |  |  | cubicle of the 22 kV Indoor switchgear and the power transformers
352 |  | - | Outdoor cable termination kit, 22 kV, for the H.V. power cable | 9 | Set
353 |  |  | of copper conductor size 500 sq.mm., completed with accessories.
354 |  | - | Indoor cable termination kit, 22 kV, for the H.V. power cable | 9 | Set
355 |  |  | of copper conductor size 500 sq.mm., completed with accessories.
356 |  | - | H.V. power cable, 3-1x50 sq.mm., 22 kV, for connecting between the station | 1 | Lot
357 |  |  | service transformer unit cubicle of the 22 kV Indoor switchgear and the
358 |  |  | station service transformer
359 |  | - | Outdoor cable termination kit, 22 kV, for the H.V. power | 3 | Set
360 |  |  | cable of copper conductor size 50 sq.mm., completed with accessories.
361 |  | - | Indoor cable termination kit, 22 kV, for the H.V. power | 3 | Set
362 |  |  | cable of copper conductor size 50 sq.mm., completed with accessories.
363 | 13 | Aluminium conductor & accessories
364 |  | - | Stranded conductor, aluminium, 400 SQ.mm. and accessories | 1 | Lot
365 |  | - | Substation connectors. | 1 | Lot
366 |  | - | Stranded conductor accessories. | 1 | Lot
367 | 14 | Cable ladder & conduit for substation
368 |  | - | Rigid steel conduits, fittings and accessories | 1 | Lot
369 |  | - | Cable tray and cable ladder & fixing material | 1 | Lot
370 |  | - | Identification plates and danger notice. | 1 | Lot
371 |  | - | Other necessary materials. | 1 | Lot
372 | 15 | Grounding system
373 |  | - | Ground mesh for 115 kV substation | 1 | Lot
374 |  | - | Earthing system in switchyard. (structure and equipments) | 1 | Lot
375 |  | - | Earthing system in control building. | 1 | Lot
376 |  | - | Ground rod, copper cover steel, dia. 16 mm. 3 m. long. | 30 | pcs
377 |  | - | Conductor, copper, bare 95 sq.mm. | 1 | Lot
378 |  | - | Earthing test pit. | 1 | Unit
379 | 16 | Over head ground wire system
380 |  | - | Wire, steel stranded 50/7 sq.mm. and accessories | 1 | Lot
381 |  | - | Concrete pole 14.00 m, foundation and accessories | 1 | Set
382 |  | - | Insulator suspension type, and string assemblies. | 1 | Lot
383 | 17 | Substation lighting
384 |  | - | 100 watt, LED lamp post. | 4 | Set
385 |  | - | Lamp post and floodlight timing control panel | 1 | Set
386 | 18 | Cable & accessories for substation
387 |  | - | LV power cable, 750 V, for connecting between the station service transformer and | 1 | Lot
388 |  |  | AC distribution board.
389 |  | - | LV power cable, 750 V, for connecting between AC distribution board and all AC | 1 | Lot
390 |  |  | consumer, battery and battery charger, battery charger and safety switch with fuse,
391 |  |  | DC distribution board and battery charger.
392 |  | - | LV power cable, 750 V, for connecting between the AC distribution boards and | 1 | Lot
393 |  |  | substation lighting
394 |  | - | LV power cable, 750 V, for connecting between the AC, DC distribution board and | 1 | Lot
395 |  |  | 22 kV switchgear, control board.
396 |  | - | Control cable, 750 V, for connecting between the instrument transformers and the | 1 | Lot
397 |  |  | control board.
398 |  | - | Control cable, 750 V, for connecting between the control board and switchyard | 1 | Lot
399 |  |  | equipment
400 | 19 | Accessories |  | 1 | Lot
401 | 20 | Factory test, commissioning and training
402 |  | - | Factory test (battery charger, AC and DC distribution board) | 1 | Lot
403 |  | - | Function & Commissioning test | 1 | Lot
404 |  | - | Generator & distribution transformer for back energize to 22 kV switchgear and | 1 | Lot
405 |  |  | transfer to 115 kV side by power transformer
406 |  | PART B งานโยธาสถานีไฟฟ้า
407 | 1 | Sub-soil test from ground surface |  | 1 | Lot | By PEA
408 | 2 | Earth work and compact soil
409 |  | - | Clear space on 22x30 Sq.mm. | 1 | Lot | By Owner
410 |  | - | Compact soil | 1 | Lot | By Owner
411 | 3 | Control building
412 |  | - | Control building 5 x 12 x (1.6+4.5) m., (w x l x h) | 1 | Lot
413 |  | - | Control building pile and foundation | 1 | Lot
414 |  | - | Epoxy floor (green/red colour) self leveling type | 1 | Lot
415 |  | - | Earthing system in control building 25x4 mm. steel strip & 6 sets of busbar ground, | 1 | Lot
416 |  |  | PVC, RSC and accessories
417 | 4 | Faciltity for control building
418 |  | - | 2x36 watt LED lighting fixture with reflector | 11 | Set
419 |  | - | 2x36 watt LED lighting fixture with reflector explosion proof | 1 | Set
420 |  | - | 1x36 watt LED lighting fixture (wp) | 4 | Set
421 |  | - | Receptacle | 6 | Set
422 |  | - | Air condition 36,000 Btu | 2 | Set
423 |  | - | Air condition control panel | 1 | Set
424 |  | - | Ventilation (Fan) and hood for rain protection | 2 | Set
425 |  | - | Emergency lighting 2x50 w | 3 | Set
426 |  | - | Switch, wire, conductor, conduits and accessories | 1 | Lot
427 |  | - | Fire Extinguisher (CO2) | 2 | Set
428 | 5 | Fire alarm system
429 |  | - | Hardwire system 2 zone (manual ,detector) | 1 | Set
430 |  | - | Smoke detector (control building) | 4 | Set
431 |  | - | Heat detector (battery room) | 1 | set
432 |  | - | Bell alarm | 1 | Set
433 |  | - | Fire resistance wire conductor, wire conductor, conduits and accessories | 1 | Lot
434 | 6 | 115-22 kV transformer foundation with RC. oil gutter., on pile |  | 1 | Set
435 | 7 | Steel cover around of RC. oil gutter (installation on RC oil gutter) |  | 1 | Lot
436 | 8 | Oil collecting pit and oil separator capacity not less than 20 cu.m., on pile |  | 1 | Set
437 | 9 | 2 set of steel pipes dia 6 inch |  | 10 | m
438 | 10 | Station service transformer foundation on pile |  | 1 | Set
439 | 11 | Switchyard and foundation on pile
440 |  | - | 115 kV Take-off structure foundation | 2 | Set
441 |  | - | 115 kV Disconnecting switch foundation | 1 | Set
442 |  | - | 115 kV Current transformer foundation | 3 | Set
443 |  | - | 115 kV Inductive voltage transformer foundation | 3 | Set
444 |  | - | 115 kV Circuit-breaker foundation | 1 | Set
445 |  | - | Operating platform foundation | 3 | Set
446 | 13 | Lamp post foundation, on pile |  | 4 | Set
447 | 14 | Cable trench with steel cover, size 0.80 m |  | 1 | Lot
448 | 15 | Cable trench with steel cover, size 0.80 m., T-shape |  | 1 | Set
449 | 16 | Cable trench with steel cover, size 1.20 m. |  | 1 | Lot
450 | 17 | HDPE Dia 63 mm. PN8 and accessories (for lamp post circuit) |  | 1 | Lot
451 | 18 | Crushed rock no.2 surfacing on area 23x32 m., 0.10 m hight with concrete curb |  | 1 | Lot
452 | 19 | RC Trench with RC cover or PVC pipe in substation (for rain drainge system) |  | 1 | Lot
453 | 20 | RC pipe, PVC. pipe and RC manhole (All drainage system from control building, |  | 1 | Lot
454 |  | RC trench, oil collecting pit and oil separator etc.)
455 | 21 | Wiremesh fench |  | 1 | Lot
456 | 22 | Mesh gate (1 set x rolling door) 6.00 m width |  | 1 | Set
457 | 23 | Mesh gate (1 set) 1.00 m width |  | 1 | Set
458 | 24 | Civil engineering design and construction permissive fee (architech , civil , electrical) |  | 1 | Lot
459 | 25 | Temporary fence and toilet |  | 1 | Lot
460 |  | Part C งานก่อสร้างสายส่งระบบ 115 เควี (ภายใน)
461 | 1 | Civil work
462 |  | - | Concrete pole 22 m. Long | 1 | Each
463 |  | - | Pole foudation type F5, grounding type D-25E with GR-1 | 1 | Set
464 | 2 | Electrical work
465 |  | - | Top pole installation type SS-SW-2 (115 kV Air break switch supply by PEA) | 1 | Set
466 |  | - | Steel support for 115 kV Air break switch | 1 | Set
467 |  | - | 400 sq.mm. AAC | 1 | Lot
468 |  | - | Wire,steel stranded 35 sqmm. | 1 | Lot
469 |  | - | Operating platform for 115 kV Air break switch | 1 | Set | By PEA | By PEA
470 | 3 | Accessories |  | 1 | Lot
471 | 4 | Other
472 |  | - | คืนสภาพพื้นที่การก่อสร้างทั้งโครงการ ตลอดจน ถนน และ/หรือ ต้นไม้ , สนามหญ้า | 1 | Lot | Include | Include
473 |  | - | อุปกรณ์ป้องกันงูชนิดแผ่นอลูมิเนียมและตาข่ายสำหรับเสาคอนกรีตทุกต้น | 1 | Lot | Include
474 |  | - | อุปกรณ์ป้องกันงูชนิดกรวยอลูมิเนียมสำหรับสายยึดโยงทุกเส้น | 1 | Lot | Include
475 |  | - | พ่นสีแสดงหมายเลขเสา ชนิดของหัวเสา และฐานราก | 1 | Lot | Include
476 |  | - | Accessories | 1 | Lot | Include
477 |  | Part D งานก่อสร้างระบบจำหน่าย 22 เควี
478 | 1 | ช่วง A - B
479 | 1.1 | 22 kV Distribution System
480 |  | - | Concrete Pole 14.30 m Long | 5 | Set
481 |  | - | 22 kV Load Break Switch , 600A with local control cubicle | 2 | Set
482 |  | - | Top pole installation : X-arm-C SP | 4 | Set
483 |  | - | Top pole installation : X-arm-C DDE | 4 | Set
484 |  | - | Top pole installation : X-arm-C BL | 2 | Set
485 |  | - | Cable aerial, SAC 1x185 sq.mm. | 1 | Lot
486 |  | - | Wire,steel stranded 25 sqmm. | 1 | Lot
487 |  | - | Grounding and accessories | 1 | Lot
488 |  | - | Guy and accessories | 1 | Lot
489 |  | - | Modify top pole installation : DE/DE/LBS to be DE,BA/DE,BA/LBS | 1 | Lot
490 | 1.2 | 22 kV Riser Pole (RS-F1-1, RS-F2-1) |  | 2 | Set
491 |  | - | 1 Set of Concrete Pole 14.30 m Long
492 |  | - | 3 Set of Termination kit supporting device
493 |  | - | 3 Set of Lightning arrester 21 kV, 10 kA and supporting frame
494 |  | - | 3 Set of 22 kV Disconnecting switch 600A and supporting frame
495 |  | - | Cable grip, HDPE conduit, Steel guard
496 |  | - | Insulator, Crossarm, OHGW and accessories
497 |  | - | Grounding and accessories
498 | 1.3 | Cable trench with steel cover, size 1.50 m. |  | 1 | Lot
499 | 1.4 | Power cable & termination kit
500 |  | - | H.V. power cable, 3-1x240 sq.mm., 22 kV, for connecting between the 22 kV indoor | 1 | Lot
501 |  |  | switchgear outgoing 1 cubicle of the and riser pole RS-F1-1, the 22 kV indoor switchgear
502 |  |  | outgoing 2 cubicle of the and riser pole RS-F2-1
503 |  | - | Outdoor cable termination kit, 22 kV, for the H.V. power cable | 6 | Lot
504 |  |  | of copper conductor size 240 sq.mm., completed with accessories.
505 |  | - | Indoor cable termination kit, 22 kV, for the H.V. power cable | 6 | Lot
506 |  |  | of copper conductor size 240 sq.mm., completed with accessories.
507 | 1.5 | Connecting new 22 kV distribution line to existing |  | 1 | Lot | Include
508 | 2 | ช่วง B - C
509 | 2.1 | 22 kV Underground System
510 |  | - | Handhole type 3 (HH-3) without pile | 2 | Set
511 |  | - | 10-160mm. HDPE, HDD from handhole no.1 and handhole no.2 | 1 | Lot
512 |  | - | 2x1-160mm. HDPE, Ductbank from handhole no.2 to riser pole RS-F1-2, RS-F2-2, | 1 | Lot
513 |  |  | RS-Spare-1, RS-Spare-3
514 |  | - | Grounding and accessories | 1 | Lot
515 | 2.2 | 22 kV Riser Pole (RS-F1-2, RS-F2-2, RS-Spare-1, RS-Spare-2) |  | 4 | Set
516 |  | - | 1 Set of Concrete Pole 12.20 m Long
517 |  | - | 3 Set of Termination kit supporting device
518 |  | - | 3 Set of Lightning arrester 21 kV, 10 kA and supporting frame
519 |  | - | 3 Set of 22 kV Disconnecting switch and supporting frame
520 |  | - | Cable grip, HDPE conduit, Steel guard
521 |  | - | Insulator, Crossarm, OHGW and accessories
522 |  | - | Grounding and accessories
523 | 2.3 | Power cable & termination kit
524 |  | - | H.V. power cable, 3-1x240 sq.mm., 22 kV, for connecting between riser pole RS-F1-1 | 1 | Lot
525 |  |  | and riser pole RS-F1-2, riser pole RS-F2-1 and riser pole RS-F2-2
526 |  | - | Outdoor cable termination kit, 22 kV, for the H.V. power cable | 24 | Lot
527 |  |  | of copper conductor size 240 sq.mm., completed with accessories.
528 | 3 | ช่วง C - D - E
529 | 3.1 | Steel tower
530 |  | - | Steel Tower 16.00 m Long | 2 | Set
531 |  | - | Foundation of Steel Tower on pile | 2 | Set
532 |  | - | Grounding and accessories | 1 | Lot
533 | 3.2 | 22 kV Distribution System
534 |  | - | Concrete Pole 12.20 m Long | 18 | Set
535 |  | - | Top pole installation : Corner bracket 5-60 degree for 22 kV SAC | 34 | Set
536 |  | - | Top pole installation : X-arm-C DDE | 7 | Set
537 |  | - | Top pole installation : X-arm-C DDE (To install X-arm-C only) | 2 | Set
538 |  | - | Top pole installation : X-arm-C DE | 1 | Set
539 |  | - | Remove a top pole : X-arm-C DE/BA (Existing) | 1 | Set
540 |  | - | Renovate existing 22 kV distribution system 2 feeder (move position on pole) | 1 | Lot
541 |  | - | Cable aerial, SAC 1x185 sq.mm. | 1 | Lot
542 |  | - | Alluminum conductor steel rainforce, ACSR 1x185 sq.mm. | 1 | Lot
543 |  | - | Wire,steel stranded 25 sqmm. | 1 | Lot
544 |  | - | Lightning arrester 21 kV, 10 kA and supporting frame | 6 | Set
545 |  | - | Grounding and accessories | 1 | Lot
546 |  | - | Guy and accessories | 1 | Lot
547 | 3.3 | Connecting new 22 kV distribution line to existing |  | 1 | Lot | Include
548 | 4 | ช่วง D - E
549 |  | - | Remove exisiting 22 kV distribution system 1 feeder | 1 | Lot | None
550 | 5 | Control & Interlock panel for 22 kV load break switch & 22 kV switchgear |  | 1 | Lot
551 |  | - | 1 set of Programmable logic control, PLC for interlocking between existing 22 kV
552 |  |  | switchgear/22 kV load break switch and new 22 kV switchgear/22 kV load break switch
553 |  | - | 1 set of Control & interlocking panel
554 |  | - | 1 lot of control cable and communication cable
555 | 6 | Accessories |  | 1 | Lot
556 | 7 | Tools
557 |  | - | ถุงมือยาง ความยาว 14 นิ้ว (สามารถทนแรงดันไฟฟ้าได้) | 1 | Set
558 |  | - | ถุงมือหนัง | 1 | Set
559 |  | - | Disconnect stick 2PC of 1 1/4" x 8' and 1PC of 1 1/2 x 8' (3 piece) : CHANCE | 1 | Set
560 | 8 | Other
561 |  | - | คืนสภาพพื้นที่การก่อสร้างทั้งโครงการ ตลอดจน ถนน และ/หรือ ต้นไม้ , สนามหญ้า | 1 | Lot | Include
562 |  | - | อุปกรณ์ป้องกันงูชนิดแผ่นอลูมิเนียมและตาข่ายสำหรับเสาคอนกรีตทุกต้น | 1 | Lot | Include
563 |  | - | อุปกรณ์ป้องกันงูชนิดกรวยอลูมิเนียมสำหรับสายยึดโยงทุกเส้น | 1 | Lot | Include
564 |  | - | พ่นสีแสดงหมายเลขเสา ชนิดของหัวเสา และฐานราก | 1 | Lot | Include
565 |  | - | Accessories | 1 | Lot | Include
566 |  | PART E อุปกรณ์สำนักงานสำหรับใช้หน้างาน
567 | 1 | เช่ารถยนต์ส่วนบุคคล
568 |  | - | เช่ารถยนต์ส่วนบุคคล (รถเก๋ง) เกียร์ออโต้ 4 ประตู 4 ที่นั่ง 1,600 ซีซี | 1 | Lot
569 |  |  | พร้อม พรบ. ประกันชั้น 1 (อายุไม่เกิน 2 ปี) และภาษีประจำปี นาน 6 เดือน
570 |  |  | จำนวน 1 คัน และต้องเป็นรถยนต์จากบริษัทที่ดำเนินธุรกิจรถยนต์เช่า
571 | 2 | อุปกรณ์ประกอบการใช้งานสนาม
572 |  | - | เช่าตู้ Mobile Office | 1 | Lot
573 |  | - | ตู้เก็บเอกสารชนิดประตูเลื่อนกระจก ความกว้าง 1.2 เมตร จำนวน 2-3 ชั้น | 2 | Set
574 |  | - | ตู้เก็บลูกกุญแจ | 1 | Set
575 |  | - | แม่กุญแจพร้อมลูกกุญแจ จำนวน 20 ชุด และลูกกุญแจชนิดมาสเตอร์ จำนวน 3 ดอก | 1 | Lot
576 |  | - | แบบ Relaying & metering diagram for exisiting and new substation (as-built drawing) | 1 | Lot
577 |  |  | ชนิดกระดาษขาว ขนาด A1 ใส่กรอบกระจก

## Sheet2
การไฟฟ้าส่วนภูมิภาค รายละเอียดของงานเพื่อขออนุมัติเบิกจ่ายเงิน
งานก่อสร้างสถานีไฟฟ้าชนิด Outdoor AIS ระบบ 115-22 เควี, สายส่งระบบ 115 เควี (ภายใน) และระบบจำหน่าย 22 เควี ให้บริษัท มูราตะ อิเล็กทรอนิกส์ (ประเทศไทย) จำกัด จังหวัดลำพูน
| สัญญาเลขที่ กส2/2562 ลงวันที่ 24/06/2562 ผู้รับจ้าง บริษัท มูราตะ อิเล็กทรอนิกส์ (ประเทศไทย) จำกัด จังหวัดลำพูน | [7 empty] | ค่าติดตั้งและทดสอบ | งวดที่ | 2
id | ลำดับที่ | รายละเอียด |  | งานตามสัญญา |  |  |  | รวมงานที่ส่งมอบแล้ว |  | ส่งมอบงานครั้งนี้
|  |  |  | จำนวน | หน่วย | ราคาติดตั้งทดสอบ/หน่วย (บาท) | เป็นเงิน (บาท) | จำนวน | เป็นเงิน (บาท) | จำนวน | เป็นเงิน (บาท)
299 |  | PART A อุปกรณ์สถานีไฟฟ้า
300 | 1 | 115 kV Tower incoming structure ( Take off structure )
301 |  | - | 115 kV. Take-off structure, beam. | 1 | Set | 250000 | 250000 |  |  | 1 | 250000
302 |  | - | 115 kV. Take-off structure, column. | 2 | Set | 250000 | 500000 |  |  | 3 | 750000
303 |  | - | Insulator, suspension type, class 52-3, for 115 kV string assemblies. | 6 | Set
304 |  | - | 250 watt, area LED floodlight luminaires and accessories | 2 | Set
305 | 2 | 115 kV Disconnecting with grounding switch and support structure
306 |  | - | 123 kV, 1250A 40kA Disconnecting switch, three-pole, double side break with grounding | 1 | Set
307 |  |  | creepage 25 mm/kV., handle for cranking and tools
308 |  | - | 115 kV Disconnecting switch supporting structure | 1 | Set
309 |  | - | Operating platform | 2 | Set
310 | 3 | 115 kV Current transformer
311 |  | - | 115 kV Current transformer, single-phase, 4 cores, 40kA and creepage 25 mm/kV | 3 | Set
312 |  | - | 115 kV Current transformer supporting structure | 3 | Set
313 |  | - | Junction box for 115 kV current transformer | 1 | Unit
314 |  | - | Junction box supporting structure | 1 | Set
315 | 4 | 115 kV Inductive voltage transformer
316 |  | - | 115 kV Inductive voltage transformer, single-phase, 3 winding 40kA and creepage 25 mm/kV | 3 | Set
317 |  | - | 115 kV Inductive voltage transformer supporting structure | 3 | Set
318 |  | - | Junction box for 115 kV inductive voltage transformer | 1 | Unit
319 |  | - | Junction box supporting structure | 1 | Set
320 | 5 | 115 kV Gas circuit breaker (SF6)
321 |  | - | 115 kV Circuit-breaker, SF6 gas, three-pole, 3150A, 40 kA | 1 | Set
322 |  | - | 115 kV Circuit-breaker supporting structure | 1 | Set
323 |  | - | Operating platform (2 step stairs) | 1 | Set
324 | 6 | 115 kV Control & protection board
325 |  | - | Transformer control and protection board | 1 | Unit
326 |  | - | Outdoor alarm (horn & siren) | 1 | Set
327 | 7 | Power transformer
328 |  | - | 115/22 kV, 3 phase, ONAN/ONAF, 50/60 MVA, Dyn1, with automatic OLTC with | 1 | Unit
329 |  |  | oil purifier for OLTC, CT core in MV for winding temp, AVR and N bushing for protection
330 |  | - | Local control cubicle with lamp indicator and annunciator | 1 | Unit
331 |  | - | Loose supply for tap position indicator for OLTC and AVR, | 1 | Lot
332 |  | - | 108 kV 10 kA Lightning arrester and counter with supporting on power transformer | 3 | Set
333 | 8 | 22 kV Indoor air insulated switchgear (2,500 A, 25 kA, 1 Sec)
334 |  | - | 22 kV Incoming cubicle with potential transformer (2500A) | 1 | Unit
335 |  | - | 22 kV Outgoing cubicle (630A 25kA) | 2 | Unit
336 |  | - | 22 kV Load break switch cubicle with fuse 1 set | 1 | Lot
337 |  | - | Arc detection system (fiber optic 3 compartment per 1 cubicle), | 1 | Lot
338 |  | - | Wall plate for tool storage | 1 | Set
339 | 9 | 22/0.4 kV Station service transformer
340 |  | - | Station service transformer, oil-immersed type,three-phase, 50 kVA, Dyn1 | 1 | Set
341 |  |  | 22,000-400/230 VAC with cable connection boxes, for outdoor installation.
342 | 10 | AC and DC distribution board
343 |  | - | AC distribution board (2 main CB, 80 A, 20 branch circuits) | 1 | Set
344 |  | - | DC distribution board (2 main CB, 40 A, 20 branch circuits) | 1 | Set
345 | 11 | Battery & battery charger for 125 VDC
346 |  | - | Sealed lead acid battery > 58 Ah 12V/block (125 Vdc) | 1 | Lot
347 |  | - | Batter charger 30 A with automatic dropper switch | 2 | Set
348 |  | - | Safety switch with fuse | 1 | Set
349 | 12 | Power cable & termination kit
350 |  | - | H.V. power cable, 9-1x500 sq.mm., 22 kV, for connecting between the incoming | 1 | Lot
351 |  |  | cubicle of the 22 kV Indoor switchgear and the power transformers
352 |  | - | Outdoor cable termination kit, 22 kV, for the H.V. power cable | 9 | Set
353 |  |  | of copper conductor size 500 sq.mm., completed with accessories.
354 |  | - | Indoor cable termination kit, 22 kV, for the H.V. power cable | 9 | Set
355 |  |  | of copper conductor size 500 sq.mm., completed with accessories.
356 |  | - | H.V. power cable, 3-1x50 sq.mm., 22 kV, for connecting between the station | 1 | Lot
357 |  |  | service transformer unit cubicle of the 22 kV Indoor switchgear and the
358 |  |  | station service transformer
359 |  | - | Outdoor cable termination kit, 22 kV, for the H.V. power | 3 | Set
360 |  |  | cable of copper conductor size 50 sq.mm., completed with accessories.
361 |  | - | Indoor cable termination kit, 22 kV, for the H.V. power | 3 | Set
362 |  |  | cable of copper conductor size 50 sq.mm., completed with accessories.
363 | 13 | Aluminium conductor & accessories
364 |  | - | Stranded conductor, aluminium, 400 SQ.mm. and accessories | 1 | Lot
365 |  | - | Substation connectors. | 1 | Lot
366 |  | - | Stranded conductor accessories. | 1 | Lot
367 | 14 | Cable ladder & conduit for substation
368 |  | - | Rigid steel conduits, fittings and accessories | 1 | Lot
369 |  | - | Cable tray and cable ladder & fixing material | 1 | Lot
370 |  | - | Identification plates and danger notice. | 1 | Lot
371 |  | - | Other necessary materials. | 1 | Lot
372 | 15 | Grounding system
373 |  | - | Ground mesh for 115 kV substation | 1 | Lot
374 |  | - | Earthing system in switchyard. (structure and equipments) | 1 | Lot
375 |  | - | Earthing system in control building. | 1 | Lot
376 |  | - | Ground rod, copper cover steel, dia. 16 mm. 3 m. long. | 30 | pcs
377 |  | - | Conductor, copper, bare 95 sq.mm. | 1 | Lot
378 |  | - | Earthing test pit. | 1 | Unit
379 | 16 | Over head ground wire system
380 |  | - | Wire, steel stranded 50/7 sq.mm. and accessories | 1 | Lot
381 |  | - | Concrete pole 14.00 m, foundation and accessories | 1 | Set
382 |  | - | Insulator suspension type, and string assemblies. | 1 | Lot
383 | 17 | Substation lighting
384 |  | - | 100 watt, LED lamp post. | 4 | Set
385 |  | - | Lamp post and floodlight timing control panel | 1 | Set
386 | 18 | Cable & accessories for substation
387 |  | - | LV power cable, 750 V, for connecting between the station service transformer and | 1 | Lot
388 |  |  | AC distribution board.
389 |  | - | LV power cable, 750 V, for connecting between AC distribution board and all AC | 1 | Lot
390 |  |  | consumer, battery and battery charger, battery charger and safety switch with fuse,
391 |  |  | DC distribution board and battery charger.
392 |  | - | LV power cable, 750 V, for connecting between the AC distribution boards and | 1 | Lot
393 |  |  | substation lighting
394 |  | - | LV power cable, 750 V, for connecting between the AC, DC distribution board and | 1 | Lot
395 |  |  | 22 kV switchgear, control board.
396 |  | - | Control cable, 750 V, for connecting between the instrument transformers and the | 1 | Lot
397 |  |  | control board.
398 |  | - | Control cable, 750 V, for connecting between the control board and switchyard | 1 | Lot
399 |  |  | equipment
400 | 19 | Accessories |  | 1 | Lot
401 | 20 | Factory test, commissioning and training
402 |  | - | Factory test (battery charger, AC and DC distribution board) | 1 | Lot
403 |  | - | Function & Commissioning test | 1 | Lot
404 |  | - | Generator & distribution transformer for back energize to 22 kV switchgear and | 1 | Lot
405 |  |  | transfer to 115 kV side by power transformer
406 |  | PART B งานโยธาสถานีไฟฟ้า
407 | 1 | Sub-soil test from ground surface |  | 1 | Lot
408 | 2 | Earth work and compact soil
409 |  | - | Clear space on 22x30 Sq.mm. | 1 | Lot
410 |  | - | Compact soil | 1 | Lot
411 | 3 | Control building
412 |  | - | Control building 5 x 12 x (1.6+4.5) m., (w x l x h) | 1 | Lot
413 |  | - | Control building pile and foundation | 1 | Lot
414 |  | - | Epoxy floor (green/red colour) self leveling type | 1 | Lot
415 |  | - | Earthing system in control building 25x4 mm. steel strip & 6 sets of busbar ground, | 1 | Lot
416 |  |  | PVC, RSC and accessories
417 | 4 | Faciltity for control building
418 |  | - | 2x36 watt LED lighting fixture with reflector | 11 | Set
419 |  | - | 2x36 watt LED lighting fixture with reflector explosion proof | 1 | Set
420 |  | - | 1x36 watt LED lighting fixture (wp) | 4 | Set
421 |  | - | Receptacle | 6 | Set
422 |  | - | Air condition 36,000 Btu | 2 | Set
423 |  | - | Air condition control panel | 1 | Set
424 |  | - | Ventilation (Fan) and hood for rain protection | 2 | Set
425 |  | - | Emergency lighting 2x50 w | 3 | Set
426 |  | - | Switch, wire, conductor, conduits and accessories | 1 | Lot
427 |  | - | Fire Extinguisher (CO2) | 2 | Set
428 | 5 | Fire alarm system
429 |  | - | Hardwire system 2 zone (manual ,detector) | 1 | Set
430 |  | - | Smoke detector (control building) | 4 | Set
431 |  | - | Heat detector (battery room) | 1 | set
432 |  | - | Bell alarm | 1 | Set
433 |  | - | Fire resistance wire conductor, wire conductor, conduits and accessories | 1 | Lot
434 | 6 | 115-22 kV transformer foundation with RC. oil gutter., on pile |  | 1 | Set
435 | 7 | Steel cover around of RC. oil gutter (installation on RC oil gutter) |  | 1 | Lot
436 | 8 | Oil collecting pit and oil separator capacity not less than 20 cu.m., on pile |  | 1 | Set
437 | 9 | 2 set of steel pipes dia 6 inch |  | 10 | m
438 | 10 | Station service transformer foundation on pile |  | 1 | Set
439 | 11 | Switchyard and foundation on pile
440 |  | - | 115 kV Take-off structure foundation | 2 | Set
441 |  | - | 115 kV Disconnecting switch foundation | 1 | Set
442 |  | - | 115 kV Current transformer foundation | 3 | Set
443 |  | - | 115 kV Inductive voltage transformer foundation | 3 | Set
444 |  | - | 115 kV Circuit-breaker foundation | 1 | Set
445 |  | - | Operating platform foundation | 3 | Set
446 | 13 | Lamp post foundation, on pile |  | 4 | Set
447 | 14 | Cable trench with steel cover, size 0.80 m |  | 1 | Lot
448 | 15 | Cable trench with steel cover, size 0.80 m., T-shape |  | 1 | Set
449 | 16 | Cable trench with steel cover, size 1.20 m. |  | 1 | Lot
450 | 17 | HDPE Dia 63 mm. PN8 and accessories (for lamp post circuit) |  | 1 | Lot
451 | 18 | Crushed rock no.2 surfacing on area 23x32 m., 0.10 m hight with concrete curb |  | 1 | Lot
452 | 19 | RC Trench with RC cover or PVC pipe in substation (for rain drainge system) |  | 1 | Lot
453 | 20 | RC pipe, PVC. pipe and RC manhole (All drainage system from control building, |  | 1 | Lot
454 |  | RC trench, oil collecting pit and oil separator etc.)
455 | 21 | Wiremesh fench |  | 1 | Lot
456 | 22 | Mesh gate (1 set x rolling door) 6.00 m width |  | 1 | Set
457 | 23 | Mesh gate (1 set) 1.00 m width |  | 1 | Set
458 | 24 | Civil engineering design and construction permissive fee (architech , civil , electrical) |  | 1 | Lot
459 | 25 | Temporary fence and toilet |  | 1 | Lot
460 |  | Part C งานก่อสร้างสายส่งระบบ 115 เควี (ภายใน)
461 | 1 | Civil work
462 |  | - | Concrete pole 22 m. Long | 1 | Each
463 |  | - | Pole foudation type F5, grounding type D-25E with GR-1 | 1 | Set
464 | 2 | Electrical work
465 |  | - | Top pole installation type SS-SW-2 (115 kV Air break switch supply by PEA) | 1 | Set
466 |  | - | Steel support for 115 kV Air break switch | 1 | Set
467 |  | - | 400 sq.mm. AAC | 1 | Lot
468 |  | - | Wire,steel stranded 35 sqmm. | 1 | Lot
469 |  | - | Operating platform for 115 kV Air break switch | 1 | Set
470 | 3 | Accessories |  | 1 | Lot
471 | 4 | Other
472 |  | - | คืนสภาพพื้นที่การก่อสร้างทั้งโครงการ ตลอดจน ถนน และ/หรือ ต้นไม้ , สนามหญ้า | 1 | Lot | Include
473 |  | - | อุปกรณ์ป้องกันงูชนิดแผ่นอลูมิเนียมและตาข่ายสำหรับเสาคอนกรีตทุกต้น | 1 | Lot
474 |  | - | อุปกรณ์ป้องกันงูชนิดกรวยอลูมิเนียมสำหรับสายยึดโยงทุกเส้น | 1 | Lot
475 |  | - | พ่นสีแสดงหมายเลขเสา ชนิดของหัวเสา และฐานราก | 1 | Lot
476 |  | - | Accessories | 1 | Lot
477 |  | Part D งานก่อสร้างระบบจำหน่าย 22 เควี
478 | 1 | ช่วง A - B
479 | 1.1 | 22 kV Distribution System
480 |  | - | Concrete Pole 14.30 m Long | 5 | Set
481 |  | - | 22 kV Load Break Switch , 600A with local control cubicle | 2 | Set
482 |  | - | Top pole installation : X-arm-C SP | 4 | Set
483 |  | - | Top pole installation : X-arm-C DDE | 4 | Set
484 |  | - | Top pole installation : X-arm-C BL | 2 | Set
485 |  | - | Cable aerial, SAC 1x185 sq.mm. | 1 | Lot
486 |  | - | Wire,steel stranded 25 sqmm. | 1 | Lot
487 |  | - | Grounding and accessories | 1 | Lot
488 |  | - | Guy and accessories | 1 | Lot
489 |  | - | Modify top pole installation : DE/DE/LBS to be DE,BA/DE,BA/LBS | 1 | Lot
490 | 1.2 | 22 kV Riser Pole (RS-F1-1, RS-F2-1) |  | 2 | Set
491 |  | - | 1 Set of Concrete Pole 14.30 m Long
492 |  | - | 3 Set of Termination kit supporting device
493 |  | - | 3 Set of Lightning arrester 21 kV, 10 kA and supporting frame
494 |  | - | 3 Set of 22 kV Disconnecting switch 600A and supporting frame
495 |  | - | Cable grip, HDPE conduit, Steel guard
496 |  | - | Insulator, Crossarm, OHGW and accessories
497 |  | - | Grounding and accessories
498 | 1.3 | Cable trench with steel cover, size 1.50 m. |  | 1 | Lot
499 | 1.4 | Power cable & termination kit
500 |  | - | H.V. power cable, 3-1x240 sq.mm., 22 kV, for connecting between the 22 kV indoor | 1 | Lot
501 |  |  | switchgear outgoing 1 cubicle of the and riser pole RS-F1-1, the 22 kV indoor switchgear
502 |  |  | outgoing 2 cubicle of the and riser pole RS-F2-1
503 |  | - | Outdoor cable termination kit, 22 kV, for the H.V. power cable | 6 | Lot
504 |  |  | of copper conductor size 240 sq.mm., completed with accessories.
505 |  | - | Indoor cable termination kit, 22 kV, for the H.V. power cable | 6 | Lot
506 |  |  | of copper conductor size 240 sq.mm., completed with accessories.
507 | 1.5 | Connecting new 22 kV distribution line to existing |  | 1 | Lot
508 | 2 | ช่วง B - C
509 | 2.1 | 22 kV Underground System
510 |  | - | Handhole type 3 (HH-3) without pile | 2 | Set
511 |  | - | 10-160mm. HDPE, HDD from handhole no.1 and handhole no.2 | 1 | Lot
512 |  | - | 2x1-160mm. HDPE, Ductbank from handhole no.2 to riser pole RS-F1-2, RS-F2-2, | 1 | Lot
513 |  |  | RS-Spare-1, RS-Spare-3
514 |  | - | Grounding and accessories | 1 | Lot
515 | 2.2 | 22 kV Riser Pole (RS-F1-2, RS-F2-2, RS-Spare-1, RS-Spare-2) |  | 4 | Set
516 |  | - | 1 Set of Concrete Pole 12.20 m Long
517 |  | - | 3 Set of Termination kit supporting device
518 |  | - | 3 Set of Lightning arrester 21 kV, 10 kA and supporting frame
519 |  | - | 3 Set of 22 kV Disconnecting switch and supporting frame
520 |  | - | Cable grip, HDPE conduit, Steel guard
521 |  | - | Insulator, Crossarm, OHGW and accessories
522 |  | - | Grounding and accessories
523 | 2.3 | Power cable & termination kit
524 |  | - | H.V. power cable, 3-1x240 sq.mm., 22 kV, for connecting between riser pole RS-F1-1 | 1 | Lot
525 |  |  | and riser pole RS-F1-2, riser pole RS-F2-1 and riser pole RS-F2-2
526 |  | - | Outdoor cable termination kit, 22 kV, for the H.V. power cable | 24 | Lot
527 |  |  | of copper conductor size 240 sq.mm., completed with accessories.
528 | 3 | ช่วง C - D - E
529 | 3.1 | Steel tower
530 |  | - | Steel Tower 16.00 m Long | 2 | Set
531 |  | - | Foundation of Steel Tower on pile | 2 | Set
532 |  | - | Grounding and accessories | 1 | Lot
533 | 3.2 | 22 kV Distribution System
534 |  | - | Concrete Pole 12.20 m Long | 18 | Set
535 |  | - | Top pole installation : Corner bracket 5-60 degree for 22 kV SAC | 34 | Set
536 |  | - | Top pole installation : X-arm-C DDE | 7 | Set
537 |  | - | Top pole installation : X-arm-C DDE (To install X-arm-C only) | 2 | Set
538 |  | - | Top pole installation : X-arm-C DE | 1 | Set
539 |  | - | Remove a top pole : X-arm-C DE/BA (Existing) | 1 | Set
540 |  | - | Renovate existing 22 kV distribution system 2 feeder (move position on pole) | 1 | Lot
541 |  | - | Cable aerial, SAC 1x185 sq.mm. | 1 | Lot
542 |  | - | Alluminum conductor steel rainforce, ACSR 1x185 sq.mm. | 1 | Lot
543 |  | - | Wire,steel stranded 25 sqmm. | 1 | Lot
544 |  | - | Lightning arrester 21 kV, 10 kA and supporting frame | 6 | Set
545 |  | - | Grounding and accessories | 1 | Lot
546 |  | - | Guy and accessories | 1 | Lot
547 | 3.3 | Connecting new 22 kV distribution line to existing |  | 1 | Lot
548 | 4 | ช่วง D - E
549 |  | - | Remove exisiting 22 kV distribution system 1 feeder | 1 | Lot
550 | 5 | Control & Interlock panel for 22 kV load break switch & 22 kV switchgear |  | 1 | Lot
551 |  | - | 1 set of Programmable logic control, PLC for interlocking between existing 22 kV
552 |  |  | switchgear/22 kV load break switch and new 22 kV switchgear/22 kV load break switch
553 |  | - | 1 set of Control & interlocking panel
554 |  | - | 1 lot of control cable and communication cable
555 | 6 | Accessories |  | 1 | Lot
556 | 7 | Tools
557 |  | - | ถุงมือยาง ความยาว 14 นิ้ว (สามารถทนแรงดันไฟฟ้าได้) | 1 | Set | None
558 |  | - | ถุงมือหนัง | 1 | Set | None
559 |  | - | Disconnect stick 2PC of 1 1/4" x 8' and 1PC of 1 1/2 x 8' (3 piece) : CHANCE | 1 | Set | None
560 | 8 | Other
561 |  | - | คืนสภาพพื้นที่การก่อสร้างทั้งโครงการ ตลอดจน ถนน และ/หรือ ต้นไม้ , สนามหญ้า | 1 | Lot
562 |  | - | อุปกรณ์ป้องกันงูชนิดแผ่นอลูมิเนียมและตาข่ายสำหรับเสาคอนกรีตทุกต้น | 1 | Lot
563 |  | - | อุปกรณ์ป้องกันงูชนิดกรวยอลูมิเนียมสำหรับสายยึดโยงทุกเส้น | 1 | Lot
564 |  | - | พ่นสีแสดงหมายเลขเสา ชนิดของหัวเสา และฐานราก | 1 | Lot
565 |  | - | Accessories | 1 | Lot
566 |  | PART E อุปกรณ์สำนักงานสำหรับใช้หน้างาน
567 | 1 | เช่ารถยนต์ส่วนบุคคล
568 |  | - | เช่ารถยนต์ส่วนบุคคล (รถเก๋ง) เกียร์ออโต้ 4 ประตู 4 ที่นั่ง 1,600 ซีซี | 1 | Lot
569 |  |  | พร้อม พรบ. ประกันชั้น 1 (อายุไม่เกิน 2 ปี) และภาษีประจำปี นาน 6 เดือน
570 |  |  | จำนวน 1 คัน และต้องเป็นรถยนต์จากบริษัทที่ดำเนินธุรกิจรถยนต์เช่า
571 | 2 | อุปกรณ์ประกอบการใช้งานสนาม
572 |  | - | เช่าตู้ Mobile Office | 1 | Lot
573 |  | - | ตู้เก็บเอกสารชนิดประตูเลื่อนกระจก ความกว้าง 1.2 เมตร จำนวน 2-3 ชั้น | 2 | Set
574 |  | - | ตู้เก็บลูกกุญแจ | 1 | Set
575 |  | - | แม่กุญแจพร้อมลูกกุญแจ จำนวน 20 ชุด และลูกกุญแจชนิดมาสเตอร์ จำนวน 3 ดอก | 1 | Lot
576 |  | - | แบบ Relaying & metering diagram for exisiting and new substation (as-built drawing) | 1 | Lot
577 |  |  | ชนิดกระดาษขาว ขนาด A1 ใส่กรอบกระจก